## Sheet1
Term Sheet -- Construction and Installation Service Agreement (CA)
No. | General information | Value | Notes
Project name
Project location
| Head contract |  | (Name of the head contract counterparty, if this is a subcontract)
Capacity (kWp or MW)
| Contract no. |  | 8 digits: first 2 start from 01; digits 4-6 are day/month/year (2 digits each)
| Contract date |  | Must be consistent with the last 6 digits of the contract no.
Owner
| Owner registration no. |  | 13 digits
| Owner authorised signatory(ies) |  | Full name(s), matching the company's signing authority
| Owner power-of-attorney signatory |  | If signing is delegated
Owner registered office
Contractor
| Contractor registration no. |  | 13 digits
| Contractor authorised signatory(ies) |  | Full name(s), matching the company's signing authority
| Contractor power-of-attorney signatory |  | If signing is delegated
Contractor registered office
| SA counterparty |  | Name of the company with the SA with the Contractor
| SA date |  | Date the Owner signed the SA with PRG
1 | Construction and Installation Terms
| Roof / site owner |  | Name of the roof owner (Owner's company, or whoever the Owner designates)
2 | Attachments |  | Clauses may be added or removed
| Attachment 1 |  | Drawings and specifications
| Attachment 2 |  | Bill of quantities, prices of materials and equipment, and labour (BOQ)
| Attachment 3 |  | Quotation
| Attachment 4 |  | Scope of work
| Attachment 5 |  | Project Schedule
| Attachment 6 |  | Term of Reference (TOR)
3 | Contract Price
Contract Price (number)
| Contract Price (in words) |  | 2 decimal places
| VAT treatment |  | inclusive / exclusive
| Number of installments | 7
| % of installment value | Payment condition | Supporting documents
| Installment 1 (10%) | Within 10 working days of both Parties signing this Agreement and the Contractor mobilising to the project site. | (1) Electrical drawings and Single Line Diagram delivered to the Owner (2) Shop Drawings delivered to the Owner for approval (3) Pre-work site survey and roof inspection report delivered to the Owner
| Installment 2 (10%) | On completion and the Owner's acceptance of: (1) walkway installation (2) life line installation (3) mounting installation (4) Inspection Report delivered | Inspection Report
| Installment 3 (10%) | On completion and the Owner's acceptance of: (1) inverter room construction (2) inverter and inverter rack installation (3) DC combiner box installation (4) main distribution board / CB box installation (if any) (5) Inspection Report delivered | Inspection Report
| Installment 4 (10%) | On completion and the Owner's acceptance of: (1) AC electrical system installation (2) AC cable tray and conduit installation (3) grid code equipment (RPR, PQ meter, revenue meter) installation (4) Inspection Report delivered | Inspection Report
| Installment 5 (10%) | On completion and the Owner's acceptance of: (1) PV module installation (2) Inspection Report delivered | Inspection Report
| Installment 6 (10%) | On completion and the Owner's acceptance of: (1) DC cable tray and conduit installation (2) DC electrical system and grounding system installation (3) PV water cleaning system installation (4) service ladder installation (5) weather station and monitoring equipment fully operational on the Solar Monitoring System (6) Inspection Report delivered | Inspection Report
| Installment 7 (40 %) | Full handover under this Agreement and the System is able to supply power to the project, and the Owner has accepted all work: (1) Solar Monitoring System fully installed to the Owner's standard (2) building construction/modification/demolition permit (Or.1) obtained (3) Commissioning Test completed (4) signed As-Built Drawing with engineer's licence copy delivered (5) Completion of Punch List report delivered (6) site demobilisation completed (7) PR Test completed and equipment removed from site (8) Inspection Report delivered | (1) Inspection Report, Test & Commissioning Report (2) Weather Station and monitoring equipment fully operational with the Monitoring System installed to standard (3) Punch List Report and As-Built Drawing must be signed with the engineer's licence copy attached (4) panels cleaned before handover, equipment removed from site
4 | Owner's Representations |  | Additional conditions beyond the standard draft may be added here, by the User, for Legal to review
5 | Taxation and Statutory Fees
6 | Completion Deadline
| Start date |  | DD Month YYYY
| Completion date |  | DD Month YYYY
7 | Contractor Personnel Responsibility |  | Additional conditions beyond the standard draft may be added here, by the User, for Legal to review
8 | Confidentiality and Use of Information |  | Additional conditions beyond the standard draft may be added here, by the User, for Legal to review
9 | Suspension of Works |  | Additional conditions beyond the standard draft may be added here, by the User, for Legal to review
10 | Inspection of Works |  | Additional conditions beyond the standard draft may be added here, by the User, for Legal to review
11 | Discrepancy in Work Drawings |  | Additional conditions beyond the standard draft may be added here, by the User, for Legal to review
12 | Breach and Termination |  | Additional conditions beyond the standard draft may be added here, by the User, for Legal to review
13 | Force Majeure |  | Additional conditions beyond the standard draft may be added here, by the User, for Legal to review
14 | Notice
Owner contact name
Owner contact position
Owner contact location
Owner contact phone
Owner contact email
Contractor contact name
Contractor contact position
Contractor contact location
Contractor contact phone
Contractor contact email
15 | Miscellaneous |  | Additional conditions beyond the standard draft may be added here, by the User, for Legal to review
| governing law | Thailand
16 | Signatories
Owner company name
Owner signatory name
Contractor company name
Contractor signatory name